## Read Me
PPS / Elmiron Platform - Project Tracker
16-week MVP - 3 developers - v1.0
PROJECT START (Monday of Week 1) | 2026-08-10 | <- EDIT THIS. Every date in the tracker is calculated from it.
STATUS SUMMARY
Total tasks | 103
Not Started | 103
In Progress | 0
Blocked | 0
Done | 0
READY TO START NOW | 3
Waiting on a dependency | 100
% Complete | 0%
TASKS BY ROLE
Backend | 39 tasks / 0 done
Frontend | 33 tasks / 0 done
AI/Data | 31 tasks / 0 done
HOW TO USE THIS FILE
Task Tracker |  | The master list. Only edit the Status, Owner and Notes columns. Everything else is calculated.
Can Start? column |  | Calculated. READY means its dependency is Done. WAITING means it is not. Filter on READY to see what can begin today.
Status dropdown |  | Not Started / In Progress / Blocked / Done. Setting a task to Done releases everything that depends on it.
Dates |  | Calculated from the project start date above. Change that one cell and the whole schedule moves.
Timeline |  | Week-by-week view of who is doing what. Read-only summary.
Gates |  | Six checkpoints. Do not start the next phase until the gate passes. The reviewer runs the test - never accept a report.
Interfaces |  | Four contracts between the three roles, with due dates. Miss one and two people stall.
Decisions |  | Locked decisions and open blockers. O1 and O2 are blocking work right now.
Risks |  | Ranked. Owner named. Review weekly.
Cut Order |  | Agreed in advance. When the schedule slips, cut from the top. Never negotiate this in the moment.
EDIT ONLY THESE |  | Yellow = you edit. Everything else is a formula - overwriting it breaks the tracker.

## Task Tracker
ID | Week | Phase | Role | Task | Depends On | Can Start? | Status | Owner | Start | Due | Notes
BE-01 | 1 | P0 Foundations | Backend | Monorepo: Turborepo + pnpm workspaces, strict TS, lint/format | — | READY | Not Started |  | 2026-08-10 | 2026-08-16
BE-02 | 1 | P0 Foundations | Backend | CI/CD: GitHub Actions - typecheck, lint, tests on every PR | BE-01 | WAITING | Not Started |  | 2026-08-10 | 2026-08-16
BE-03 | 1 | P0 Foundations | Backend | Two Supabase projects: Mumbai + US. Same migrations, separate data. | — | READY | Not Started |  | 2026-08-10 | 2026-08-16 | Never one multi-region DB
BE-04 | 1 | P0 Foundations | Backend | Auth + 9 roles + user_profiles table | BE-03 | WAITING | Not Started |  | 2026-08-10 | 2026-08-16
BE-05 | 1 | P0 Foundations | Backend | PUBLISH packages/core types (contract I1) | BE-04 | WAITING | Not Started |  | 2026-08-10 | 2026-08-16 | DUE FRI W1 - frontend blocked without it
FE-01 | 1 | P0 Foundations | Frontend | Expo scaffold + Expo Router inside the monorepo | BE-01 | WAITING | Not Started |  | 2026-08-10 | 2026-08-16
FE-02 | 1 | P0 Foundations | Frontend | Next.js App Router scaffold | BE-01 | WAITING | Not Started |  | 2026-08-10 | 2026-08-16
FE-03 | 1 | P0 Foundations | Frontend | Token pipeline: design-tokens.json to Tailwind + RN theme | FE-02 | WAITING | Not Started |  | 2026-08-10 | 2026-08-16 | Needs design D1
AI-01 | 1 | P0 Foundations | AI/Data | Data model design review with Backend | — | READY | Not Started |  | 2026-08-10 | 2026-08-16 | Can start day 1 alongside Backend
AI-02 | 1 | P0 Foundations | AI/Data | Analytics event schema definition | AI-01 | WAITING | Not Started |  | 2026-08-10 | 2026-08-16 | Get it right now - retrofit is expensive
BE-06 | 2 | P0 Foundations | Backend | Commercial schema: orgs, territories, doctors, visits, beat plans, content | BE-04 | WAITING | Not Started |  | 2026-08-17 | 2026-08-23
BE-07 | 2 | P0 Foundations | Backend | Clinical schema namespace + placeholder patients table ONLY | BE-06 | WAITING | Not Started |  | 2026-08-17 | 2026-08-23 | Deliberately incomplete - do not guess ahead
BE-08 | 2 | P0 Foundations | Backend | Row-level security policies for all 9 roles | BE-07 | WAITING | Not Started |  | 2026-08-17 | 2026-08-23 | THE core deliverable
BE-09 | 2 | P0 Foundations | Backend | Audit log: DB triggers, append-only, logs reads not just writes | BE-08 | WAITING | Not Started |  | 2026-08-17 | 2026-08-23
BE-10 | 2 | P0 Foundations | Backend | Consent data model - immutable, withdrawal is a new row | BE-08 | WAITING | Not Started |  | 2026-08-17 | 2026-08-23
BE-11 | 2 | P0 Foundations | Backend | MOCK SERVER running with fixtures (contract I2) | BE-05 | WAITING | Not Started |  | 2026-08-17 | 2026-08-23 | DUE END W2 - highest-value unblocker
BE-12 | 2 | P0 Foundations | Backend | Adversarial RLS test suite - 15 attack paths must all fail | BE-08 | WAITING | Not Started |  | 2026-08-17 | 2026-08-23 | Gate 0 evidence
FE-04 | 2 | P0 Foundations | Frontend | Shell navigation both platforms | FE-03 | WAITING | Not Started |  | 2026-08-17 | 2026-08-23
FE-05 | 2 | P0 Foundations | Frontend | Layout primitives + component library wiring | FE-04 | WAITING | Not Started |  | 2026-08-17 | 2026-08-23 | Needs design D2
FE-06 | 2 | P0 Foundations | Frontend | Connect to mock server end to end | BE-11 | WAITING | Not Started |  | 2026-08-17 | 2026-08-23 | Do NOT build screens yet
AI-03 | 2 | P0 Foundations | AI/Data | Audit log capture design review | AI-02 | WAITING | Not Started |  | 2026-08-17 | 2026-08-23
AI-04 | 2 | P0 Foundations | AI/Data | Seed + test data generator (deterministic, re-runnable) | AI-02 | WAITING | Not Started |  | 2026-08-17 | 2026-08-23 | Gate 0 test suite needs this
BE-13 | 3 | P1 Commercial | Backend | Doctor, territory, beat-plan APIs | BE-12 | WAITING | Not Started |  | 2026-08-24 | 2026-08-30
BE-14 | 3 | P1 Commercial | Backend | Geo check-in/out API with work-hours enforcement | BE-13 | WAITING | Not Started |  | 2026-08-24 | 2026-08-30 | Hard stop outside shift window
BE-15 | 3 | P1 Commercial | Backend | Aggregation contract I3 published to AI/Data | BE-12 | WAITING | Not Started |  | 2026-08-24 | 2026-08-30 | Compliance artifact - get it reviewed
FE-07 | 3 | P1 Commercial | Frontend | Field app: MR day flow shell + beat plan + today | FE-06 | WAITING | Not Started |  | 2026-08-24 | 2026-08-30 | Needs design D3
FE-08 | 3 | P1 Commercial | Frontend | Field app: geo check-in / check-out screens | FE-07 | WAITING | Not Started |  | 2026-08-24 | 2026-08-30 | One tap from doctor screen
AI-05 | 3 | P1 Commercial | AI/Data | Anonymised aggregation service | BE-15 | WAITING | Not Started |  | 2026-08-24 | 2026-08-30 | ONLY bridge across the boundary
AI-06 | 3 | P1 Commercial | AI/Data | Suppression logic - any cell under 5 patients renders as dash | AI-05 | WAITING | Not Started |  | 2026-08-24 | 2026-08-30 | No join key back to an individual
BE-16 | 4 | P1 Commercial | Backend | Offline sync protocol | BE-13 | WAITING | Not Started |  | 2026-08-31 | 2026-09-06
BE-17 | 4 | P1 Commercial | Backend | Sync conflict resolution + queue semantics | BE-16 | WAITING | Not Started |  | 2026-08-31 | 2026-09-06
FE-09 | 4 | P1 Commercial | Frontend | Field app: call report screen | FE-08 | WAITING | Not Started |  | 2026-08-31 | 2026-09-06 | MUST be completable in under 60 seconds
FE-10 | 4 | P1 Commercial | Frontend | Field app: offline UI + sync state + queue visibility | FE-09 | WAITING | Not Started |  | 2026-08-31 | 2026-09-06 | Offline is a normal state, not an error
AI-07 | 4 | P1 Commercial | AI/Data | Analytics pipeline | AI-05 | WAITING | Not Started |  | 2026-08-31 | 2026-09-06
AI-08 | 4 | P1 Commercial | AI/Data | KPI computation engine | AI-07 | WAITING | Not Started |  | 2026-08-31 | 2026-09-06
BE-18 | 5 | P1 Commercial | Backend | Manager APIs + approval hierarchy over territory subtree | BE-13 | WAITING | Not Started |  | 2026-09-07 | 2026-09-13
BE-19 | 5 | P1 Commercial | Backend | Content storage and versioning | BE-13 | WAITING | Not Started |  | 2026-09-07 | 2026-09-13
FE-11 | 5 | P1 Commercial | Frontend | Field app: digital detailing viewer + finish | FE-10 | WAITING | Not Started |  | 2026-09-07 | 2026-09-13
FE-12 | 5 | P1 Commercial | Frontend | TRACKING TRANSPARENCY SCREEN + stop confirmation | FE-11 | WAITING | Not Started |  | 2026-09-07 | 2026-09-13 | Main adoption risk - make it reassuring
AI-09 | 5 | P1 Commercial | AI/Data | Territory KPI engine | AI-08 | WAITING | Not Started |  | 2026-09-07 | 2026-09-13
AI-10 | 5 | P1 Commercial | AI/Data | Exception detection logic for manager dashboard | AI-09 | WAITING | Not Started |  | 2026-09-07 | 2026-09-13 | Show what is off-plan, not on-plan
BE-20 | 6 | P1 Commercial | Backend | API hardening + sync edge cases | BE-17 | WAITING | Not Started |  | 2026-09-14 | 2026-09-20
FE-13 | 6 | P1 Commercial | Frontend | Manager console: shell + exception-first dashboard | FE-06 | WAITING | Not Started |  | 2026-09-14 | 2026-09-20
FE-14 | 6 | P1 Commercial | Frontend | Manager console: approvals queue + route review | FE-13 | WAITING | Not Started |  | 2026-09-14 | 2026-09-20 | Charts come from AI/Data
AI-11 | 6 | P1 Commercial | AI/Data | Manager dashboard data layer | AI-10 | WAITING | Not Started |  | 2026-09-14 | 2026-09-20
AI-12 | 6 | P1 Commercial | AI/Data | Dashboard charts + data visualisation | AI-11 | WAITING | Not Started |  | 2026-09-14 | 2026-09-20 | Read dataviz guidance first
BE-21 | 7 | P2 Clinical | Backend | Clinical schema in full (Prompt 0B) | BE-20 | WAITING | Not Started |  | 2026-09-21 | 2026-09-27 | BLOCKED ON DECISION O1
BE-22 | 7 | P2 Clinical | Backend | Consent engine - versioned, clinic-initiated, withdrawable | BE-21 | WAITING | Not Started |  | 2026-09-21 | 2026-09-27
BE-23 | 7 | P2 Clinical | Backend | Patient / diagnosis / prescription APIs | BE-21 | WAITING | Not Started |  | 2026-09-21 | 2026-09-27 | Do NOT hardcode 'Elmiron' - India brands differ
FE-15 | 7 | P2 Clinical | Frontend | Patient app: enrolment via clinic code | BE-22 | WAITING | Not Started |  | 2026-09-21 | 2026-09-27
FE-16 | 7 | P2 Clinical | Frontend | Patient app: consent flow - multi-step, refusable, withdrawable | FE-15 | WAITING | Not Started |  | 2026-09-21 | 2026-09-27
AI-13 | 7 | P2 Clinical | AI/Data | Clinical aggregate layer - anonymised only | BE-21 | WAITING | Not Started |  | 2026-09-21 | 2026-09-27
BE-24 | 8 | P2 Clinical | Backend | Diary + vision check APIs | BE-23 | WAITING | Not Started |  | 2026-09-28 | 2026-10-04
BE-25 | 8 | P2 Clinical | Backend | Ophthalmic schedule engine - cadence configurable per market | BE-24 | WAITING | Not Started |  | 2026-09-28 | 2026-10-04 | US and EU labels differ
FE-17 | 8 | P2 Clinical | Frontend | Patient app: home / today | FE-16 | WAITING | Not Started |  | 2026-09-28 | 2026-10-04 | 18px min, weight 400 min, AAA contrast
FE-18 | 8 | P2 Clinical | Frontend | Patient app: weekly symptom log | FE-17 | WAITING | Not Started |  | 2026-09-28 | 2026-10-04 | Target under 45s, 3 taps, no typing
FE-19 | 8 | P2 Clinical | Frontend | Patient app: dose confirm + reminders | FE-17 | WAITING | Not Started |  | 2026-09-28 | 2026-10-04
AI-14 | 8 | P2 Clinical | AI/Data | Diary trend computation | BE-24 | WAITING | Not Started |  | 2026-09-28 | 2026-10-04
AI-15 | 8 | P2 Clinical | AI/Data | Retention instrumentation | AI-14 | WAITING | Not Started |  | 2026-09-28 | 2026-10-04 | Measure retention, do not assume it
BE-26 | 9 | P2 Clinical | Backend | AE detection engine + SLA timers computed on insert | BE-24 | WAITING | Not Started |  | 2026-10-05 | 2026-10-11 | Clock starts at insert, not triage
BE-27 | 9 | P2 Clinical | Backend | Reminder engine - administrative content only | BE-24 | WAITING | Not Started |  | 2026-10-05 | 2026-10-11 | No clinical advice text
FE-20 | 9 | P2 Clinical | Frontend | Patient app: monthly vision check - structured only | FE-18 | WAITING | Not Started |  | 2026-10-05 | 2026-10-11 | Safety critical
FE-21 | 9 | P2 Clinical | Frontend | Patient app: AE report flow + calm acknowledgement | FE-20 | WAITING | Not Started |  | 2026-10-05 | 2026-10-11 | Silence here is the worst outcome
AI-16 | 9 | P3 AI Layer | AI/Data | LLM gateway scaffold + provider abstraction | AI-13 | WAITING | Not Started |  | 2026-10-05 | 2026-10-11
AI-17 | 9 | P3 AI Layer | AI/Data | Evaluation harness for summary quality | AI-16 | WAITING | Not Started |  | 2026-10-05 | 2026-10-11 | Measured, not eyeballed
AI-18 | 9 | P3 AI Layer | AI/Data | Request/response logging + refusal handling | AI-16 | WAITING | Not Started |  | 2026-10-05 | 2026-10-11
AI-19 | 9 | P3 AI Layer | AI/Data | PUBLISH AI gateway contract I4 | AI-18 | WAITING | Not Started |  | 2026-10-05 | 2026-10-11 | DUE END W9 - frontend needs it
BE-28 | 10 | P2 Clinical | Backend | AE case export with all 4 validity elements | BE-26 | WAITING | Not Started |  | 2026-10-12 | 2026-10-18
BE-29 | 10 | P2 Clinical | Backend | Consent withdrawal handling - AE records must survive | BE-26 | WAITING | Not Started |  | 2026-10-12 | 2026-10-18 | Needs a test, not a comment
FE-22 | 10 | P2 Clinical | Frontend | Doctor console: patient list | BE-23 | WAITING | Not Started |  | 2026-10-12 | 2026-10-18
FE-23 | 10 | P2 Clinical | Frontend | Doctor console: patient detail view | FE-22 | WAITING | Not Started |  | 2026-10-12 | 2026-10-18 | Readable in 15 seconds
AI-20 | 10 | P3 AI Layer | AI/Data | PHI guard - tokenisation and stripping before egress | BE-30 | WAITING | Not Started |  | 2026-10-12 | 2026-10-18 | Highest risk component in the codebase
AI-21 | 10 | P3 AI Layer | AI/Data | Prompt design + retrieval index over approved content | AI-20 | WAITING | Not Started |  | 2026-10-12 | 2026-10-18
BE-30 | 11 | P3 AI Layer | Backend | PHI tokenisation service for the AI gateway | BE-28 | WAITING | Not Started |  | 2026-10-19 | 2026-10-25
BE-31 | 11 | P3 AI Layer | Backend | AI call audit trail - who, what data class, provider, response | BE-30 | WAITING | Not Started |  | 2026-10-19 | 2026-10-25
FE-24 | 11 | P3 AI Layer | Frontend | Doctor console: diagnosis entry | FE-23 | WAITING | Not Started |  | 2026-10-19 | 2026-10-25
FE-25 | 11 | P3 AI Layer | Frontend | Doctor console: prescription entry - brand, form, dose | FE-23 | WAITING | Not Started |  | 2026-10-19 | 2026-10-25 | Do NOT hardcode 'Elmiron'
AI-22 | 11 | P3 AI Layer | AI/Data | Patient history summary with inline citations | AI-21 | WAITING | Not Started |  | 2026-10-19 | 2026-10-25 | HCP-facing only
BE-32 | 12 | P3 AI Layer | Backend | External integration work | BE-30 | WAITING | Not Started |  | 2026-10-26 | 2026-11-01 | SCOPE BLOCKED ON DECISION O4
FE-26 | 12 | P3 AI Layer | Frontend | Doctor console: ophthalmic monitoring schedule status | BE-25 | WAITING | Not Started |  | 2026-10-26 | 2026-11-01
FE-27 | 12 | P3 AI Layer | Frontend | AISummaryCard integration | AI-19 | WAITING | Not Started |  | 2026-10-26 | 2026-11-01 | Impossible to render without citations
AI-23 | 12 | P3 AI Layer | AI/Data | Visit prep brief | AI-22 | WAITING | Not Started |  | 2026-10-26 | 2026-11-01
AI-24 | 12 | P3 AI Layer | AI/Data | OUTPUT GUARD - hard filter on advice and prediction language | AI-22 | WAITING | Not Started |  | 2026-10-26 | 2026-11-01 | A filter, not a prompt instruction
AI-25 | 12 | P3 AI Layer | AI/Data | Approved-content retrieval for the field team | AI-21 | WAITING | Not Started |  | 2026-10-26 | 2026-11-01
BE-33 | 13 | P4 Mkt/Admin | Backend | Marketing APIs | BE-20 | WAITING | Not Started |  | 2026-11-02 | 2026-11-08
BE-34 | 13 | P4 Mkt/Admin | Backend | UCPMP-aware input and sample tracking with value caps | BE-33 | WAITING | Not Started |  | 2026-11-02 | 2026-11-08
FE-28 | 13 | P3 AI Layer | Frontend | Gynaecologist referral surface | FE-23 | WAITING | Not Started |  | 2026-11-02 | 2026-11-08 | Different IA - NOT a prescribing UI
AI-26 | 13 | P3 AI Layer | AI/Data | Red-team round 1 + full gateway log review | AI-24 | WAITING | Not Started |  | 2026-11-02 | 2026-11-08 | Gate 3 evidence
BE-35 | 14 | P4 Mkt/Admin | Backend | Admin APIs + break-glass with mandatory typed reason | BE-29 | WAITING | Not Started |  | 2026-11-09 | 2026-11-15
BE-36 | 14 | P4 Mkt/Admin | Backend | Audit log viewer API | BE-35 | WAITING | Not Started |  | 2026-11-09 | 2026-11-15
FE-29 | 14 | P4 Mkt/Admin | Frontend | PV console UI - SLA clock is the primary element | BE-28 | WAITING | Not Started |  | 2026-11-09 | 2026-11-15
FE-30 | 14 | P4 Mkt/Admin | Frontend | Admin console UI - break-glass typed reason before render | BE-35 | WAITING | Not Started |  | 2026-11-09 | 2026-11-15
AI-27 | 14 | P4 Mkt/Admin | AI/Data | Marketing console + CLM telemetry processing | BE-33 | WAITING | Not Started |  | 2026-11-09 | 2026-11-15
AI-28 | 14 | P4 Mkt/Admin | AI/Data | Content performance analytics + UCPMP reporting | AI-27 | WAITING | Not Started |  | 2026-11-09 | 2026-11-15
BE-37 | 15 | P5 Hardening | Backend | Security review + dependency audit + pen test remediation | BE-36 | WAITING | Not Started |  | 2026-11-16 | 2026-11-22
BE-38 | 15 | P5 Hardening | Backend | Backup and restore TESTED (not assumed) + breach runbook | BE-37 | WAITING | Not Started |  | 2026-11-16 | 2026-11-22 | India 72hr / US 60day notification
FE-31 | 15 | P5 Hardening | Frontend | Accessibility audit + fixes, real screen reader testing | FE-30 | WAITING | Not Started |  | 2026-11-16 | 2026-11-22 | VoiceOver and TalkBack, not just automated
FE-32 | 15 | P5 Hardening | Frontend | Performance, bundle size, polish | FE-31 | WAITING | Not Started |  | 2026-11-16 | 2026-11-22
AI-29 | 15 | P5 Hardening | AI/Data | Red-team round 2 + model cost monitoring + budget alarm | AI-26 | WAITING | Not Started |  | 2026-11-16 | 2026-11-22
AI-30 | 15 | P5 Hardening | AI/Data | DPIA data-flow map support | AI-29 | WAITING | Not Started |  | 2026-11-16 | 2026-11-22
BE-39 | 16 | P6 Pilot | Backend | Pilot ops, monitoring, alerting, on-call | BE-38 | WAITING | Not Started |  | 2026-11-23 | 2026-11-29
FE-33 | 16 | P6 Pilot | Frontend | Pilot bug fixes | FE-32 | WAITING | Not Started |  | 2026-11-23 | 2026-11-29
AI-31 | 16 | P6 Pilot | AI/Data | Pilot dashboards + retention measurement | AI-30 | WAITING | Not Started |  | 2026-11-23 | 2026-11-29
Formulas:
Start = 'Read Me'!$B4+([Week]-1)*7
Due = [Start]+6

## Timeline
Week | Dates | Phase | Backend | Frontend | AI/Data | Gate
1 | 2026-08-10 | P0 Foundations | • Monorepo: Turborepo + pnpm workspaces, strict TS, lint/format • CI/CD: GitHub Actions - typecheck, lint, tests on every PR • Two Supabase projects: Mumbai + US. Same migrations, separate data. • Auth + 9 roles + user_profiles table • PUBLISH packages/core types (contract I1) | • Expo scaffold + Expo Router inside the monorepo • Next.js App Router scaffold • Token pipeline: design-tokens.json to Tailwind + RN theme | • Data model design review with Backend • Analytics event schema definition
2 | 2026-08-17 | P0 Foundations | • Commercial schema: orgs, territories, doctors, visits, beat plans, content • Clinical schema namespace + placeholder patients table ONLY • Row-level security policies for all 9 roles • Audit log: DB triggers, append-only, logs reads not just writes • Consent data model - immutable, withdrawal is a new row • MOCK SERVER running with fixtures (contract I2) • Adversarial RLS test suite - 15 attack paths must all fail | • Shell navigation both platforms • Layout primitives + component library wiring • Connect to mock server end to end | • Audit log capture design review • Seed + test data generator (deterministic, re-runnable) | G0: RLS Boundary
3 | 2026-08-24 | P1 Commercial | • Doctor, territory, beat-plan APIs • Geo check-in/out API with work-hours enforcement • Aggregation contract I3 published to AI/Data | • Field app: MR day flow shell + beat plan + today • Field app: geo check-in / check-out screens | • Anonymised aggregation service • Suppression logic - any cell under 5 patients renders as dash
4 | 2026-08-31 | P1 Commercial | • Offline sync protocol • Sync conflict resolution + queue semantics | • Field app: call report screen • Field app: offline UI + sync state + queue visibility | • Analytics pipeline • KPI computation engine
5 | 2026-09-07 | P1 Commercial | • Manager APIs + approval hierarchy over territory subtree • Content storage and versioning | • Field app: digital detailing viewer + finish • TRACKING TRANSPARENCY SCREEN + stop confirmation | • Territory KPI engine • Exception detection logic for manager dashboard
6 | 2026-09-14 | P1 Commercial | • API hardening + sync edge cases | • Manager console: shell + exception-first dashboard • Manager console: approvals queue + route review | • Manager dashboard data layer • Dashboard charts + data visualisation | G1: Offline Field Day
7 | 2026-09-21 | P2 Clinical | • Clinical schema in full (Prompt 0B) • Consent engine - versioned, clinic-initiated, withdrawable • Patient / diagnosis / prescription APIs | • Patient app: enrolment via clinic code • Patient app: consent flow - multi-step, refusable, withdrawable | • Clinical aggregate layer - anonymised only
8 | 2026-09-28 | P2 Clinical | • Diary + vision check APIs • Ophthalmic schedule engine - cadence configurable per market | • Patient app: home / today • Patient app: weekly symptom log • Patient app: dose confirm + reminders | • Diary trend computation • Retention instrumentation
9 | 2026-10-05 | P2 Clinical | • AE detection engine + SLA timers computed on insert • Reminder engine - administrative content only | • Patient app: monthly vision check - structured only • Patient app: AE report flow + calm acknowledgement | • LLM gateway scaffold + provider abstraction • Evaluation harness for summary quality • Request/response logging + refusal handling • PUBLISH AI gateway contract I4
10 | 2026-10-12 | P2 Clinical | • AE case export with all 4 validity elements • Consent withdrawal handling - AE records must survive | • Doctor console: patient list • Doctor console: patient detail view | • PHI guard - tokenisation and stripping before egress • Prompt design + retrieval index over approved content | G2: Adverse Event Path
11 | 2026-10-19 | P3 AI Layer | • PHI tokenisation service for the AI gateway • AI call audit trail - who, what data class, provider, response | • Doctor console: diagnosis entry • Doctor console: prescription entry - brand, form, dose | • Patient history summary with inline citations
12 | 2026-10-26 | P3 AI Layer | • External integration work | • Doctor console: ophthalmic monitoring schedule status • AISummaryCard integration | • Visit prep brief • OUTPUT GUARD - hard filter on advice and prediction language • Approved-content retrieval for the field team
13 | 2026-11-02 | P3 AI Layer | • Marketing APIs • UCPMP-aware input and sample tracking with value caps | • Gynaecologist referral surface | • Red-team round 1 + full gateway log review | G3: AI Red-Team
14 | 2026-11-09 | P4 Mkt/Admin | • Admin APIs + break-glass with mandatory typed reason • Audit log viewer API | • PV console UI - SLA clock is the primary element • Admin console UI - break-glass typed reason before render | • Marketing console + CLM telemetry processing • Content performance analytics + UCPMP reporting | G4: Marketing Boundary
15 | 2026-11-16 | P5 Hardening | • Security review + dependency audit + pen test remediation • Backup and restore TESTED (not assumed) + breach runbook | • Accessibility audit + fixes, real screen reader testing • Performance, bundle size, polish | • Red-team round 2 + model cost monitoring + budget alarm • DPIA data-flow map support | G5: Security
16 | 2026-11-23 | P6 Pilot | • Pilot ops, monitoring, alerting, on-call | • Pilot bug fixes | • Pilot dashboards + retention measurement | G6: Pilot

## Gates
Gate | Week | Name | Owner | Pass criteria | Warning | Status | Verified by | Date
G0 | 2 | RLS Boundary | Backend | MR / Manager / Marketing tokens denied on clinical data via REST, raw SQL, join, function and view. Audit log rejects UPDATE and DELETE. Break-glass writes audit row BEFORE returning data. | If any test passes when it should fail: STOP. Do not patch in application code. | Not Reached
G1 | 6 | Offline Field Day | Backend + Frontend | One territory runs a full simulated day offline and syncs clean. No lost writes, no duplicates, deterministic conflict resolution. Tracking policy document signed. |  | Not Reached
G2 | 10 | Adverse Event Path | Backend | Patient logs a vision symptom, flagged in minutes, lands in PV queue with running clock, mock PV officer exports a valid case with all 4 elements. Consent withdrawal does NOT delete the AE record. | IF THIS FAILS, DO NOT PROCEED TO PHASE 3. | Not Reached
G3 | 13 | AI Red-Team | AI/Data | Two independent testers must FAIL to: (a) make AI give clinical advice, (b) surface output to a patient, (c) leak an identifier to the provider, (d) produce an uncited summary. | Not run by the person who built it. | Not Reached
G4 | 14 | Marketing Boundary | Backend | A marketing user attempts to reach patient-level data by every path and fails. Suppression threshold verified on a seeded dataset. |  | Not Reached
G5 | 15 | Security | Backend | Clean pen test on all high findings. Restore performed from backup, witnessed. |  | Not Reached
G6 | 16 | Pilot | All | AE path exercised at least once with a real submission. Retention measured, not assumed. |  | Not Reached
RULE: never start the next phase until the gate passes. The reviewer runs the test personally - never accept a passing report.

## Interfaces
ID | Contract | Owner | Consumers | Due (end of week) | If it slips | Status
I1 | Typed API contract (packages/core types + Zod schemas) | Backend | Frontend, AI/Data | 1 | Frontend cannot start at all | Not Started
I2 | Mock server with realistic fixtures for every endpoint | Backend | Frontend | 2 | Frontend blocked for the whole project. The single highest-value unblocker. | Not Started
I3 | Aggregation contract - what crosses the commercial/clinical boundary, in what shape, with the suppression rule | Backend | AI/Data | 3 | AI/Data cannot build the aggregation service. This is a compliance artifact - get it reviewed. | Not Started
I4 | AI gateway contract - request/response shape, citation format, error and refusal cases | AI/Data | Frontend, Backend | 9 | AISummaryCard cannot be built against a real shape | Not Started
Never change an interface silently. Announce breaking changes in writing before they land.

## Decisions
ID | State | Decision | What it affects | Status / blocking | Owner
O1 | OPEN | Data controller model - pharma-owned vs split vs per-market | Clinical schema, consent engine, whole clinical track | BLOCKING BE-21 (week 7) | Reviewer
O2 | OPEN | Which brand, molecule and legal entity. Elmiron does not exist in India - PPS sells as Comfora, Cystopen, For-IC, Pentossan | Branding, MR content, regulatory owner | BLOCKING design + content | Reviewer
O3 | OPEN | Urologists vs gynaecologists as the detailing audience | Doctor master schema, content strategy, territory design | Needed by week 2 | Reviewer
O4 | OPEN | 'Patient interactions via API' - which system? EMR, WhatsApp, labs, pharmacy? | Integration scope: 2 weeks or 3 months | BLOCKING BE-32 (week 12) | Reviewer
O5 | OPEN | Marketing and sales data scope; source of actual sales data | Phase 4 entirely | Needed by week 4 | Reviewer
O6 | OPEN | Team skill inventory - can AI/Data do SQL and data modelling? | Validity of the whole three-role split | Needed immediately | Reviewer
O7 | OPEN | Existing 'partnering Elmiron project' - never made accessible | Greenfield vs rebuild | Repo confirms greenfield; likely closeable | Reviewer
L1 | LOCKED | AI is non-diagnostic - summarise, organise, retrieve only | No dose suggestions, no risk scores, no ranking |  | —
L2 | LOCKED | AI is HCP-facing only in v1 - patients see raw data | India TPG prohibition + FDA criterion 3 |  | —
L3 | LOCKED | LLM provider abstracted, not chosen. Zero-retention DPA required before real data |  |  | —
L4 | LOCKED | MR tracking hybrid - continuous during work hours only, hard stop after | Company devices or separated work profile |  | —
L5 | LOCKED | Web + mobile as two frontends over one shared core | Expo + Next.js, not twelve products |  | —
L6 | LOCKED | 16 weeks to pilot-ready MVP |  |  | —
L7 | LOCKED | Diary is weekly symptom log + monthly vision check, not daily | Retention evidence: median 5.5 days in the wild |  | —
L8 | LOCKED | AE routing always to a human queue, never AI-triaged |  |  | —
L9 | LOCKED | Enrolment is clinic-initiated by the treating doctor | No app-store self-signup for the clinical side |  | —

## Risks
# | Risk | Likelihood | Impact | Mitigation | Owner | Early warning sign
1 | Frontend overload from week 7 - patient app and doctor console overlap | High | High | Cut order pre-agreed. AI/Data takes all chart work. Reviewer refuses new screen requests. | Reviewer | FE behind by >3 days at the week-6 checkpoint
2 | AI/Data invents scope in weeks 3-10 | High | High | Their weeks 1-10 work is specified and gated. Weekly check they are on aggregation, not prototyping a recommender. | Reviewer | Anything appearing that is not in the plan
3 | Decision O1 unanswered at week 7 | High | High | Escalate now. Clinical schema cannot be built without it. | Reviewer | Still open at end of week 4
4 | Mock server slips past week 2 | Medium | High | Not optional. A week of blocked frontend costs more than the mock server costs to build. | Backend | Any excuse involving 'the real API is nearly ready'
5 | Nobody owns QA | High | Medium | Each role tests their own. Reviewer verifies every gate independently - runs the test, never reads the report. | Reviewer | Bugs found at pilot instead of at a gate
6 | AE volume overwhelms manual PV triage | Medium | High | Structured vision check reduces free text. SLA timers with escalation. Staff before launch, not after. | Backend | AE queue depth at pilot
7 | Backend bottleneck weeks 7-9 - clinical schema, consent and AE engine all land together | Medium | High | Densest backend stretch in the project. Consider moving the reminder engine to week 10. | Backend | BE behind at the week-8 checkpoint
8 | PHI leaks to the LLM provider | Medium | High | Gateway with tokenisation. Zero-retention DPA signed before real data. Log review at Gate 3. | AI/Data | Any identifier in a provider payload
9 | RBAC enforced in UI only, not at the database | Medium | Critical | Gate 0 is an automated adversarial test, not a code read. | Backend | Empty results where permission-denied is expected
10 | Patient retention collapses | High | High | Weekly not daily. Clinic enrolment. Human follow-up budgeted. Measure at pilot, do not assume. | AI/Data | Retention instrumentation at week 8
11 | Wrong drug, brand or legal entity (decision O2) | High | High | Answer O2 in week 1 | Reviewer | Still open at end of week 2
12 | Bus factor of 1 on every role | High | Medium | PROJECT-OVERVIEW.md appended every phase, not at the end. | All | One person off sick in week 9

## Cut Order
CUT ORDER - agreed in advance
When the schedule slips, cut from the top. Never negotiate this in the moment.
Order | Cut this | Consequence
1 | Marketing console | Manual process for the pilot
2 | Gynaecologist referral surface | Deferred to phase 2
3 | Admin console polish | Functional but plain
4 | PV console polish | Functional but plain. The SLA clock stays.
5 | Visit prep brief | History summary alone is enough for the pilot
6 | Field app: expenses, training, certification | Manual for the pilot
7 | Patient app: my-visits, help screens | Deferred
NEVER CUT
Phase 0 in any form
The Phase 2 adverse-event gate
Row-level security
The audit log
The AI output guard
Patient-app accessibility
The tracking transparency screen
These six are the difference between a product and a liability.